## Sheet1
| # | Description | Lead | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
|  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Thrust #1 | 1 | Research FRP language features and choose an appropriate host language for implementing our FRP CRN language | bar: Year 2 1 to Year 3 4
| 2 | Develop rapid prototype syntax and semantics of FRP language, assess its effectiveness, and reevaluate syntax/semantics design decisions | bar: Year 1 1 to Year 1 3; Year 3 1 to Year 3 4
| 3 | Develop complete language with prescribed features | bar: Year 1 1 to Year 2 3
Thrust #2 | 4 | Identify a set of safety properties comnonly found in CRNs | bar: Year 2 1 to Year 3 4
| 5 | Investigate methods to formally capture those properties in types | bar: Year 1 1 to Year 1 3; Year 3 1 to Year 3 4
| 6 | Design and implement a static analysis type checker for the FRP CRN language | bar: Year 1 1 to Year 2 3
Thrust #3 | 4 | Investigate requirements based on Thrust #1 and Thrust #2 (repeated throughout project based on Thrust #1 or Thrust #2 updates)
| 5 | Invetigate and architect software designs (repeated when necessary)
| 6 | Implement and debug prototype (repreated wen necessary)
Broader Impacts | 7 | Engage students in research-based training (1 Ph.D. 8+ undergraduate) | All
| 8 | Curicular material, decimination, and presentations/classes | All
| 9 | Outreach activities (public lectures, workshops, local STEM presentations) | All | bar: Year 1 1 to Year 1 2
| 10 | Publish results in journals and conferences | All | bar: Year 1 1 to Year 2 2